## Pre-Mortem
Pre-Mortem Lite, free edition from DirectorPM.com
Run this at kickoff, 60 minutes. Frame it as: it is 12 months from now and this program failed. Why? Write silently first, then cluster. The full Pre-Mortem Tool ($39 at directorpm.com/pre-mortem) adds the facilitation guide and the scripts for the awkward moments.
Imagined failure | Category | Likelihood (1-5) | Severity (1-5) | Score | Mitigation | Owner | Due date
The vendor contract is not signed before the build starts | External | 4 | 5 |  | Legal review booked for week 2; no build work until signature | A. Rivera, platform lead | 2026-03-06
Two teams assume the other owns data migration | Ownership | 4 | 4 |  | Name a single owner in the charter at kickoff, not later | D. Okonjo, delivery | 2026-02-27
The launch date was promised before scope was known | Schedule | 5 | 4 |  | Re-baseline with the sponsor now, while it is still cheap | M. Halvorsen, PM | 2026-02-20
Nobody has tested at production data volume | Technical | 3 | 5 |  | Load test in week 4 with a copy of prod | S. Beaumont, eng | 2026-03-20
The exec sponsor changes role mid-program | Political | 2 | 5 |  | Write the charter so it survives a handover; brief the deputy | M. Halvorsen, PM | 2026-03-13
Rule: any row scoring 15 or higher with no owner turns red. A failure nobody owns is the one that comes true.